## Sheet1
Sl No | Phase | Input | Activities | Responsibility | Outcome
1 | Test Planning | Project Plan | Identify the resources Team Formation Test Estimation Preparation of Test Plan Review of Test Plan Test Plan Sign-off | Test Lead (70%) | Test Plan Document
|  | Functional Requirement Specification(FRS) |  | Test Manager (30%)
Business Requirement Document(BRD)
2 | Test Designing(Test Development) | Project Plan | Prepare Test Scenarios | Test Lead | Test Case Document
|  | Functional Requirement Specification(FRS) | Prepare Test Cases | Tester | RTM
|  | Business Requirement Document(BRD) | Review Test Cases | Test Architect
|  | Test Plan | Requirement Traceability Matrix (RTM) | Test Manager
|  | Design Documents | Test Cases Sign-off
Use Cases
| Test Execution | Test Plan | Execute Test Cases
|  | Test Case Document | Find Defects | Test Lead
|  | Build / Env from Development Team | Report Defects | Tester | Test Execution Result
|  | Functional Requirement Specification(FRS) | Follow up on Defects | Test Architect | Test Report
|  | Business Requirement Document(BRD) | Close Defects | Test Manager
|  | Some specific knowledge | Test Report
| Test Closure | Test Cases | Preparation of Defect Report | Test Lead
|  | Test Reports | Evaluate your Exit Criteria | Tester | Test Summary Report
|  | Defect Reports |  | Test Architect
Test Manager